## Slide 1: JED at QCC
The JED Campus Program is a four-year collaboration between JED and key stakeholders from across the campus community to assess and strengthen mental health, substance misuse and suicide prevention systems on campus.
JED provides assessment tools, expert guidance, and customized technical assistance to support implementation of recommended practices.
A critical element of success is a shared vision that student well-being is everyone’s responsibility and linked to student and institutional success.

## Slide 2: JED 4 yr plan
The JED Campus 4-Year Timeline consists of:
Year 1 – Assessment and Strategic Planning which includes a Baseline Assessment and Healthy Minds Survey with the University of Michigan. Year 1 includes a campus site visit and strategic plan creation.
Year 2 & 3 – is all about implementing that strategic plan and utilizing various JED resources and learning opportunities.
Year 4 – is like year 1 in that we will do some post assessments and think about goal setting and sustainability after the program is wrapped up.

## Slide 3: JED Campus Visit
The JED Campus Visit took place at Queensborough Community College on Thursday, May 2nd, and Friday May 3rd. A Campus Advisor and Subject Matter Expert from JED came to campus in order to learn more about the QCC campus. They met with the JED Campus Team and shared some of the data that was collected with the group.
On the first day of the site visit, the Campus Advisor met with staff from the Counseling Center to learn more about that office. They also took a tour of the campus and held a student focus group to hear more about the student experience. On Day 2 of the Site Visit, the Campus Advisor met with the JED Campus team to lead a workshop in order to facilitate conversation and provide recommendations.

## Slide 4: HMS Study Data Highlights
Full Reports are available for viewing
Of 585 students surveyed, 27% scored 10 or higher on the GAD 7, 11% scored 15 or above
Of 604 students surveyed, 35% showed some form of depression based on the PHQ-9, 19.6% showed major depression
Of 600 responses, 15.8% reported using marijuana in the past 30 days and 17% reported binge drinking in the past 2 weeks
Of 551 students surveyed, 15% report to using psychotropic medication in the past year, of 517 who responded, 9% report that they currently use psychiatric medication
Of 606 students, 11% report suicidal ideation in the past year and 5% of 607 students actually had a plan
This data can be broken down by gender, race, years in school and more. It can also be compared to data from similar colleges.

## Slide 5: Outcome of Visit
Strategic Plan
Six Action Steps
1. Implement campus wide educational campaigns that promote shared responsibility for student emotional well-being
2. Ensure your JED Campus team has representation from diverse stakeholders across campus
3. Ensure the campus community is aware of the JED Campus strategic plan and the work of the task force
4. Collect data on student utilization and incidents on campus related to mental health/substance misuse
5. Annually analyze data that is collected by demographic group to inform strategic planning
6. Share/utilize data analysis to inform current and future mental health and substance use initiatives

## Slide 6: JED Strategic Plan
As per JED Liaison Liz Bracken: “I know it can seem daunting at first as it is very comprehensive but remember that you and your team will have three years to work on it”.
The Strategic Plan is organized by the JED Campus domain areas, and each action step has a description in the "JED Notes" column.
It will be important, as you move into the implementation phase and begin working on the strategic plan, that you provide updates in this sheet in the "Team Notes" column.
This lets us know about the progress you are making as it is getting done, which is indicated in the "Status" column as red (not started), yellow (in progress), or green (complete).
The status is determined by the questions you answered in the baseline assessment and from what I’ve learned from the campus visit. I will update it during our quarterly calls to discuss progress updates and share resources you may need.

## Slide 7: JED Strategic Plan
Strategic Planning | 1.1 | Implement campus wide educational campaigns that promote shared responsibility for student emotional well-being | JED strongly recommends that campuses communicate the story of their efforts related to mental health and emotional wellbeing. It's important that senior leadership be involved in communicating this campus-wide commitment. Here are some helpful steps: 1. Create an overall communication plan to continue to articulate that student, staff, and faculty mental health and well-being are institutional priorities that should target target faculty, staff, parents, and students. 2. Campaign messages should be sent once per semester. 3. Campaigns should explicitly include commitments to support a diverse student population. Resources & Examples: Campus President Announcement on Mental Health Awareness Month Sample Statements from JED Campuses: Mission, Values, and Vision | Red

## Slide 8
Strategic Planning | 1.2 | Ensure your JED Campus team has representation from diverse stakeholders across campus | Bringing together a cross-campus JED team reinforces your commitment to emotional health on campus as a shared responsibility. Given the complexity of the strategic tasks ahead, the size of the committee, and the amount of tasks placed on your leads, we strongly suggest forming a steering committee with individuals in leadership roles for well-defined subcommittees. JED recommends: 1. Throughout the JED Campus program, continue to monitor who should be on your JED team. Strive to get as many people represented on your task force from JED's recommendations, or that are meaningful representatives from departments that will help you push the work forward. link list of suggested team members 2. The task force includes upper administration. It would be good to identify and inform a “champion” among senior leadership to help establish a solid communication flow about JED initiatives and progress. Communications templates for senior leadership can be found in the JED Campus Playbook. One idea discussed during your campus visit was to involve students in this work wherever appropriate. Resources & Examples: Building Your JED Campus Team | Yellow

## Slide 9
Strategic Planning | 1.3 | Ensure the campus community is aware of the JED Campus strategic plan and the work of the task force | Develop strategies for maintaining the momentum created in the initial campus visit. This will include strong messaging about a JED Campus campaign to senior leadership and members of the community. You will want to establish priorities to be delegated to subcommittees who can then support your efforts in terms of messaging the work you are doing as part of JED Campus. JED recommends: 1. Sharing the strategic plan with faculty, staff, students, and the rest of the campus community such as alumni and families/caregivers. 2. Leadership should annually update faculty, staff, students, and parents on strategic plan progress. Many campuses create a JED website and house it either within their counseling webpage or a separate webpage on their college website. This can include information about JED Campus, information on your strategic plan, links to health and wellness resources on campus, a list of JED Campus team members, etc. 3. The JED Campus strategic plan should be integrated with the institution’s broader strategic plan. This serves both to share with the campus the work your team is doing as well as to make your institutional priority clear. During your campus visit, one breakout group shared the importance of ensuring communicaitons are available in multiple languages for a variety of audiences. Resources & Examples: Communication Toolkit Sample School Websites and Statements | Red

## Slide 10
Strategic Planning | 1.4 | Collect data on student utilization and incidents on campus related to mental health/substance misuse | Consider all the methods you are utilizing to collect data. Consider also the different software being used for tracking of mental health and substance misuse incidents. It would be good to collect data on mental health services utilization, substance misuse service utilization, incidents related to mental health, and incidents related to substance use. Consider ways in which data could be better collected and consolidated in one location or software. You have some good data collected currently and it would be worth creating a plan now of who will analyze this data and utilize it to direct our work going forward. | Yellow

## Slide 11: Next Steps
Strategic Planning | 1.5 | Annually analyze data that is collected by demographic group to inform strategic planning | As you move forward with implementing action steps from the JED work, consider keeping ways to evaluate the effectiveness of programs already in place and those that you implement from this process. JED recommends analyzing data related to mental health and substance misuse by: 1. gender 2. race/ethnicity 3. country of origin 4. sexual orientation 5. gender identity 6. first generation status 7. veteran status 8. other groups deemed as a priority | Yellow

## Slide 12
Strategic Planning | 1.6 | Share/utilize data analysis to inform current and future mental health and substance use initiatives | As you analyze your data, make sure you are utilizing it to inform the direction of your team and any future work you do as part of the JED Campus program. Consider ways to utilize the data you collect to better promote all of the efforts already occurring on your campus as well as to identify any gaps in support that could be beneficial to your students. It would be good to share the data: 1. publicly via a website 2. in presentations to upper administration 3. in presentations for boards of trustees 4. at conferences and other professional organization events 5. in quality improvement working groups on campus to improve services Resources & Examples: Using Data to Engage Campu Stakeholders in JED Campus Work | Yellow

## Slide 13: Next Steps
Teams formed to tackle specific objectives